## Sheet1
S.No | Date | Tabs | Problem Description | Status | Priority | Category
1 | 28.07.2026 | Dashboard – Overview | During testing, it was identified that the SLA at Risk, My Timesheet Compliance, Missing Timesheet Team, and Unresolved Action options are not in use. | Completed | P2 | Bug
2 | 28.07.2026 | My Workspace - My Assignment section | The Task Status filter displays only the "Open" and "Active" statuses. Other task status options are not displayed | Yet To Start | P2 | Bug
3 | 28.07.2026 | Tickets - All Tickets | During testing, it was identified that the At Risk, and On Hold options are not in use. | Completed | P2 | Bug
4 | 28.07.2026 | Tickets - Create Ticket | As discussed, are forwarded tickets considered assigned tickets? If so, how are tickets assigned? | Completed | P2 | New Feature
5 | 28.07.2026 | Tickets - Create Ticket - Save as Draft | The "Save as Draft" functionality is not working while creating a ticket | Completed | P2 | Bug
6 | 28.07.2026 | Create Ticket - Attachment Create Project - Attachment | The Attachment functionality has not been confirmed during testing in both the Create Ticket and Create Project modules | Yet To Start | P1 | Bug
7 | 29.07.2026 | Reports | The report data is displayed correctly in the Ticketing Tool web page. However, when the report is downloaded in Excel or PDF format, the details are not captured correctly | Yet To Start | P2 | Bug
8 | 29.07.2026 | Tickets - All Tickets | Manual timesheet entry is not available. Only the automatic timer option is provided for recording timesheet entries. | Completed | P1 | New Feature
9 | 29.07.2026 | Project - All Project - Create Task - Sub Task | It was identified that the Hard Dependency and Soft Dependency options are not working while creating a subtask | Completed | P2 | Bug
10 | 29.07.2026 | Project - All Project - Create Task | It was identified that the system allows users to create a task with a date earlier than the project creation date. | Completed | P1 | Bug
11 | 29.07.2026 | Tickets | It was identified that, after creating a task, only the Owner and Coordinator are displayed in the ticket. The other team members added during task creation are not displayed. However, when the ticket is linked to the project, it is visible to all project members. | Tickets,My Workspace → Tickets lists the ticket for every selected team member. Create Task → Assignee lists all selected team members, not only owner/coordinator. Completed | P1 | New Feature
12 | 30.07.2026 | My Workspace - Tickets | Without assigning the newly create ticket to the project we cannot create task | Completed | P1 | New Feature
13 | 30.07.2026 | My Workspace - Tickets | Manual timesheet entry is not available. Only the automatic timer option is provided for recording timesheet entries. | Completed | P1 | New Feature
14 | 31.07.2026 | My Workspace - Tickets and Projects | It was observed that the Assignee field does not list the team members added to the ticket during task creation. |  | P1 | Bug
15 | 31.07.2026 | My Workspace - Tickets and Projects | It was identified that when the Ticket Owner creates a task and assigns it to a team member, the task is visible only to the assigned team member and is not visible to the Ticket Owner |  | P1 | Bug
16 | 31.07.2026 | My Workspace - Tickets and Projects | It was observed that after a ticket is created and assigned to team members, if one team member creates a subtask and assigns it to another team member, the assignee can view the subtask but cannot log time in the Timesheet. |  | P1 | Bug
17 | 31.07.2026 | My Workspace - Tickets and Projects | Currently, the Ticket and Project modules allow only a single timesheet entry. It is recommended to provide an option to edit timesheet entries, as this would improve usability and help users correct or update their logged time |  | P2 | New Feature